## Contents
Department of Families, Fairness and Housing 2020-21 Annual Report – machine readable dataset
Capital Projects
Contents
Capital Projects
Accessibility
To receive this data in another format, email "DFFH Corporate Reporting (DFFH)" <DFFHcorporate.reporting@dffh.vic.gov.au>
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Health logo), this work, Department of Health annual report 2020–21, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Health) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people. ‘Indigenous’ or ’Koori/Koorie’ is retained when part of the title of a report, program or quotation.
ISSN 2653-1976 – Online (pdf / word) (2107071)
Available at Department of Families, Fairness and Housing annual reports <https://www.dffh.vic.gov.au/publications/annual-reports-department-families-fairness-housing>

## Capital Projects
Capital projects reaching practical completion during the financial year ended 30 June 2021
Project name | Original comple-tion date | Latest approved comple-tion date | Practical comple-tion date | Reason for variance in completion dates | Original approved TEI budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Acquisition general construction 2020-21 (statewide) | 2021-06-01 | 2021-06-01 | 2021-06-01 |  | 16 | 16 | 16
High-rise upgrades in 2020–21 (metropolitan various) | 2021-06-01 | 2021-06-01 | 2021-06-01 |  | 12 | 12 | 12
Low-rise upgrades in 2020–21 (statewide) | 2021-06-01 | 2021-06-01 | 2021-06-01 |  | 59.524 | 59.524 | 59.524