## Contents
Department of Families, Fairness and Housing 2023-24 Annual Report – machine readable dataset
Capital projects
Contents
Capital Projects
Accessibility
To receive this publication in an accessible format, email DFFHcorporate.reporting@dffh.vic.gov.au.
Authorised and published by the Victorian Government, 1 Treasury Place, Melbourne.
© State of Victoria, Australia (Department of Family, Fairness and Housing), November 2024.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Families, Fairness and Housing logo), this work, Department of Families, Fairness and Housing Annual Report 2023-24, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Families, Fairness and Housing) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people. ‘Indigenous’ or ’Koori/Koorie’ is retained when part of the title of a report, program or quotation.
ISSN 2653-1976 – Online (pdf/word) (2107071)
Available at Department of Families, Fairness and Housing Services annual reports <www.dffh.vic.gov.au/publications/annual-reports-department-families-fairness-housing>.

## Capital projects
Capital projects / asset investment programs
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved TEI budget | Latest approved TEI budget | Actual TEI cost | Variation between actual cost and latest approved TEI budget | Reason for variance from latest approved TEI budget
[5 empty] | ($m) | ($m) | ($m) | ($m)
Base Housing Renewal 2023–24 (statewide) | Q4 2024 | 2024-06-01 | 2024-06-01 | – | 81.5 | 99.2 | 98.5 | -0.7 | Project completed under budget
Big Housing Build physical improvements (statewide) | Q4 2027 | 2024-06-01 | 2024-06-01 | – | 184 | 184 | 184 | 0
Carlton Redevelopment – 246 units/sites (North-West metropolitan) | Q4 2019 | 2024-03-01 | 2024-03-01 | – | 146.4 | 149.1 | 145.8 | -3.3 | Project completed under budget
Minor capital works 2023–2024 (statewide) | Q4 2024 | 2024-06-01 | 2024-06-01 | – | 24.1 | 24.1 | 24.1 | 0
Social Housing Pipeline Projects (statewide) | Q4 2021 | 2024-06-01 | 2024-06-01 | – | 14.7 | 16 | 15.3 | -0.7 | Project completed under budget
Supporting homelessness services in Victoria (statewide) | Q4 2024 | 2024-06-01 | 2024-06-01 | – | 22.9 | 22.9 | 22.9 | 0
Westmeadows redevelopment 110 units/sites (Westmeadows) | Q4 2019 | 2024-06-01 | 2024-03-01 | – | 54.9 | 72.8 | 71.2 | -1.6 | Project completed under budget