## Contents
Department of Families, Fairness and Housing 2024–25 Annual Report – machine readable dataset
Capital projects
Contents
Capital Projects/asset investment programs
Accessibility
To receive this publication in an accessible format, email DFFHcorporate.reporting@dffh.vic.gov.au.
Authorised and published by the Victorian Government, 1 Treasury Place, Melbourne.
Copyright
© State of Victoria, Australia (Department of Family, Fairness and Housing), October 2025.
CC-BY
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Families, Fairness and Housing logo), this work, Department of Families, Fairness and Housing Annual Report 2024–25, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability, are available at Creative Commons Attribution 4.0 International.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Families, Fairness and Housing) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people. ‘Indigenous’ or ‘Koori/Koorie’ is retained when part of the title of a report, program or quotation.
ISSN 2653-1976 – Online (pdf/word) (2507388)
Available at Department of Families, Fairness and Housing Services annual reports <www.dffh.vic.gov.au/publications/annual-reports-department-families-fairness-housing>

## Capital Projects
Capital projects / asset investment programs
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved TEI budget ($m) | Latest approved TEI budget ($m) | Actual TEI cost ($m) | Variation between actual cost and latest approved TEI budget ($m) | Reason for variance from latest approved TEI budget
Building works stimulus (statewide) | qtr 4 2021–22 | qtr 2 2024–25 | 2024-12-01 | – | 155 | 177.2 | 175.5 | 1.7 | Variance is less than 1% of TEI with final expenditure expected for projects in 2025–26.
Housing Renewals 2024–25 (statewide) | qtr 4 2024–25 | qtr 4 2024–25 | 2025-06-01 | – | 70.6 | 18.9 | 14 | 4.9 | Program scope delivered within TEI. Surplus funds were reprioritised.
Housing Upgrades 2024–25 (statewide) | qtr 4 2024–25 | qtr 4 2024–25 | 2025-06-01 | – | 24.5 | 28.1 | 28.1 | – | N/A
Investing to make homelessness rare, brief and non-recurring (statewide) | qtr 4 2022–23 | qtr 4 2027–28 | 2028-06-01 | – | 24 | 0 | 0 | –