## Contents
Department of Health and Human Services annual report 2019-20 – machine readable dataset:
Capital projects reaching practical completion
Contents
Capital projects reaching practical completion during the financial year ended 30 June 2020
Accessibility
To receive this data in another format, email corporate reporting
<corporate.reporting@dhhs.vic.gov.au>.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or
the Department of Health and Human Services logo), this work, Department of Health and Human Services annual report
2019–20 dataset portfolio budget outcomes, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at
Creative Commons Attribution 4.0 International
<https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia with the other licence terms.
(Department of Health and Human Services) as the author and/or owner of the work, indicate if any changes have been made to the work and comply
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people.
‘Indigenous’ or ‘Koori/Koorie’ is retained when part of the title of a report, program or quotation.
Available at Department of Health and Human Services annual reports
<https://www.dhhs.vic.gov.au/publications/annual-reports>

## Capital projects
Capital projects reaching practical completion during the financial year ended 30 June 2020
Project name | Original comple-tion date | Latest approved comple-tion date | Practical comple-tion date | Reason for variance in completion dates | Original approved TEI budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Casey Hospital Expansion | 2020-06-01 | 2020-06-01 | 2020-04-01 |  | 2.4 | 139.78 | 143.633 | 3.853 | Original TEI was for planning only. Latest approved TEI includes $5 million contribution from Monash University for accommodation space.
Austin Health Critical infrastructure | 2018-06-01 | 2020-06-01 | 2019-06-01 | Scope revised to include hydraulics works. | 40.8 | 70.616 | 62.685 | -7.931 | TEI increase to reflects additional project scope to include hydraulics works. Project in Defects Liability Period
Barwon Health – North | 2019-06-01 | 2019-08-01 | 2019-07-01 | Project achieved Practical Completion July 2019. | 28.08 | 33.08 | 30.18 | -2.9 | TEI increase to reflect additional funding for site location. Defects and Liability period will conclude July 2020.
Clinical Technology Refresh 2019–20 (statewide) | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 13 | 13 | 13
Communal Family Violence Refuges – replacement and growth program (statewide) | 2018-06-01 | 2019-09-01 | 2019-12-01 | Difficulty locating suitable sites. | 15 | 15 | 15
Efficient Government Building (statewide) | 2016-06-01 | 2019-09-01 | 2019-09-01 | Planning delays | 13.385 | 13.385 | 13.385
Forensic mental health implementation plan – priority service reforms (Footscray) | 2018-06-01 | 2020-06-01 | 2020-06-01 | Project scope was revised to include more works. | 3.9 | 5.942 | 4.645 | -1.297 | TEI was increased to include revised project scope.
Grampians Prevention and Recover Care (PARC) Services (Ballarat) | 2021-06-01 | 2021-06-01 | 2020-04-01 | The project reached practical completion in April 2020. | 6 | 6 | 5.711 | -0.289 | Project in Defects Liability Period.
High rise Upgrades in 2019–20 (metropolitan various) | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 19.27 | 19.27 | 19.27
Low rise Upgrade in 2019–20 (statewide) | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | 59.027 | 59.027 | 59.027
Royal Melbourne Hospital – critical infrastructure works | 2019-06-01 | 2019-06-01 | 2019-12-01 |  | 40 | 40 | 37.875 | -2.125 | Balance of funding is required for financial closeout of the project, noting the project has entered Defects Liability Period (DLP) which is expected to end December 2020.
Supporting Demand for Ambulance Services | 2019-06-01 | 2019-06-01 | 2019-06-01 |  | 3.345 | 3.345 | 3.349 | 0.004
The Joan Kirner Women's and Children's Hospital | 2019-06-01 | 2020-06-01 | 2020-06-01 |  | 200 | 200 | 200.112 | 0.112